Department of Technical Education

Capstone Project

Time-Line Schedule

Capstone Project Name:

Segmentation of Arecanut Bunches Using Deep Learning

Capstone Project Members:

- Bhoomika

- Divya shivayogi chouter

- Sanjana

- 1. Identify the Activities and Tasks Needed to Produce Each Work Package:

| Sl. No | Activity | Description |
| --- | --- | --- |
| 1 | Project Planning & Literature Survey | Study of image segmentation techniques and arecanut crop analysis |
| 2 | Dataset Collection | Capture images of arecanut bunches under different conditions |
| 3 | Data Annotation | Manual labelling of arecanut bunch regions |
| 4 | Image Pre-processing | Image resizing, normalization, augmentation |
| 5 | Model Selection | Selection of segmentation models (U-Net, Mask R-CNN, etc.) |
| 6 | Deep Learning Model Development | Designing and configuring the segmentation network |
| 7 | Model Training & Validation | Training model with annotated dataset |
| 8 | Performance Evaluation | IoU, Dice coefficient, accuracy evaluation |
| 9 | System Testing | Testing segmentation on unseen images |
| 10 | Documentation & Presentation | Report writing and final presentation |

2. Identify Resources for Each Task:

| Task | Time | Knowledge Required | Resources |
| --- | --- | --- | --- |
| Literature Survey | 1 Weeks | Image Processing, DL | Research papers |
| Dataset Collection | 1 Weeks | Agricultural knowledge | Mobile / Camera |
| Data Annotation | 2 Weeks | Image labelling | Labelling tools |
| Pre-processing | 2 Weeks | Python, OpenCV | Laptop |
| Model Development | 2 Weeks | CNN, Segmentation | TensorFlow / Python |
| Training | 2 Weeks | Deep Learning | GPU / Google Colab |
| Evaluation | 2 Weeks | Performance Metrics | Python |
| Documentation | 1 Weeks | Technical Writing | MS Word |

3. Estimate How Long It Will Take to Complete Each Task (Considering Constraints):

| Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning & Survey |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 Weeks |
| Dataset Collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 Weeks |
| Annotation & Pre-processing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 Weeks |
| Model Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 Weeks |
| Training & Validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 Weeks |
| Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 Weeks |
| Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 Weeks |
| Documentation & Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 Weeks |

4. Determine Task Dependencies and Develop a Critical Path:

Task Dependencies

- Literature Survey → Dataset Collection

- Dataset Collection → Annotation

- Annotation → Pre-processing

- Pre-processing → Model Development

- Model Development → Training

- Training → Evaluation

- Evaluation → Testing

- Testing → Documentation

- Critical Path:

- Survey → Dataset Collection → Annotation → Pre-processing → Training → Evaluation → Testing → Documentation

5. Develop a Schedule of Activities (Weekly and Monthly – Gantt Chart)

| Activity / Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning & Problem Formulation | ■ |  |  |  |  |  |  |  |  |  |  |  |  |
| Literature Review & Technology Study |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| Dataset Acquisition & Understanding |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |
| Image Preprocessing & Annotation |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |
| U-Net Model Design & Training |  |  |  |  |  | ■ | ■ | ■ |  |  |  |  |  |
| Model Testing & Performance Evaluation |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| Result Analysis & Optimization |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |
| Documentation & Final Submission |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |

Monthly Schedule

| Month | Activities |
| --- | --- |
| Month 1 | Project Planning, Problem Definition, Literature Survey, Technology Study |
| Month 2 | Dataset Collection, Annotation, Image Pre-processing |
| Month 3 | Deep Learning Model Development, Training, Validation |
| Month 4 | Model Testing, Performance Evaluation, Result Analysis, Documentation & Presentation |

Date:

Signature of the Student:

Signature of the Cohort Owner: